## Weeks 7 to 12
COSC2196 Project
Cool Runnings (Group 19)
| Project Start: | 2019-04-08 |  |  | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
PHASE 1 | Display Week: | 1 |  |  | 2019-04-08 | [6 empty] | 2019-04-15 | [6 empty] | 2019-04-22 | [6 empty] | 2019-04-29 | [6 empty] | 2019-05-06 | [6 empty] | 2019-05-13
Planning Timeline | time axis 2019-04-08 to 2019-05-19
TASK | PROGRESS | START | END | DAYS | time axis 2019-04-08 to 2019-05-19
Team Profile
Group Processes Reflection | 100% | 2019-04-08 | 2019-04-14 | 7
Career Plan Reflection | 100% | 2019-04-08 | 2019-04-21 | 14
Tools
Update Website | 100% | 2019-05-13 | 2019-05-19 | 7
Reflection on Audit Trail | 100% | 2019-05-13 | 2019-05-19 | 7
Project Description
Overview | 100% | 2019-04-08 | 2019-04-21 | 14
Aims | 100% | 2019-04-15 | 2019-04-21 | 7
Plans and Progress | 100% | 2019-04-15 | 2019-04-28 | 14
Roles | 100% | 2019-04-29 | 2019-05-05
Scope & Limits | 100% | 2019-04-22 | 2019-05-05 | 14
Tools & Technologies | 100% | 2019-04-29 | 2019-05-05
Testing | 100% | 2019-04-29 | 2019-05-12
Timeframe (on-going) | 100% | 2019-04-08 | 2019-05-19
Risks | 100% | 2019-05-06 | 2019-05-19
Group Communication | 100% | 2019-04-08 | 2019-04-14 | 7
Skills & Jobs
Potential Position Descriptions | 100% | 2019-05-13 | 2019-05-19 | 7
Final Report Writing
Editing/Production Copy | 100% | 2019-05-13 | 2019-05-19 | 7
2018-01-13
Formulas:
Week 7 = [Week 7, row below]
Week 8 = [Week 8, row below]
Week 9 = [Week 9, row below]
Week 10 = [Week 10, row below]
Week 11 = [Week 11, row below]
Week 12 = [Week 12, row below]
Note on F6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Weeks 13 to 22
COSC2196 Project
Cool Runnings (Group 19)
| Project Start: | 2019-05-20 |  |  | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22
PHASE 2 | Display Week: | 1 |  |  | 2019-05-20 | [6 empty] | 2019-05-27 | [6 empty] | 2019-06-03 | [6 empty] | 2019-06-10 | [6 empty] | 2019-06-17 | [6 empty] | 2019-06-24 | [6 empty] | 2019-07-01 | [6 empty] | 2019-07-08 | [6 empty] | 2019-07-15 | [6 empty] | 2019-07-22
Development & Design Timeline | time axis 2019-05-20 to 2019-07-28
TASK | PROGRESS | START | END | DAYS | time axis 2019-05-20 to 2019-07-28
Hardware Development
Feasibility Reports | 0% | 2019-05-20 | 2019-06-02 | 14
Prototyping | 0% | 2019-05-27 | 2019-06-16
Testing (local) | 0% | 2019-05-27 | 2019-06-16
Testing (remote/production) | 0% | 2019-06-17 | 2019-07-21
Revisioning Stage | 0% | 2019-06-24 | 2019-07-07
Final Product | 0% | 2019-07-01 | 2019-07-21
Manufacturing/Assembly | 0% | 2019-07-15 | 2019-07-28 | 14
Software Development
Prototyping | 0% | 2019-05-27 | 2019-06-16 | 21
Testing (local) | 0% | 2019-05-27 | 2019-06-16
Network Infrastructure | 0% | 2019-06-03 | 2019-07-21
User Interface | 0% | 2019-06-03 | 2019-07-21
Testing (remote/production) | 0% | 2019-06-17 | 2019-07-21
Revisioning Stage | 0% | 2019-06-24 | 2019-07-07
Final Product | 0% | 2019-07-01 | 2019-07-21
Deployment | 0% | 2019-07-15 | 2019-07-28
Business Relations/Partners
Market Review | 0% | 2019-05-20 | 2019-06-02 | 14
Outreach | 0% | 2019-05-27 | 2019-06-16 | 21
Customer Feedback | 0% | 2019-06-17 | 2019-07-21 | 35
Testimonials | 0% | 2019-07-15 | 2019-07-28
Presentation/Trade Show
Demo set-ups | 0% | 2019-07-22 | 2019-07-28 | 7
Posters/Paraphenalia | 0% | 2019-07-22 | 2019-07-28
2018-01-13
Formulas:
Week 13 = [Week 13, row below]
Week 14 = [Week 14, row below]
Week 15 = [Week 15, row below]
Week 16 = [Week 16, row below]
Week 17 = [Week 17, row below]
Week 18 = [Week 18, row below]
Week 19 = [Week 19, row below]
Week 20 = [Week 20, row below]
Week 21 = [Week 21, row below]
Week 22 = [Week 22, row below]
Note on F6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.